## Slide 1
PERT is a deterministic analysis tool allowing for precise times of activities within a project. False
CPM is a probabilistic analysis of managing a project. False
A PERT/CPM network is a graphical display of a project that connects activities. True
The three time estimates employed in PERT are optimistic time, most likely time, and pessimistic time. True
Slack is the time an activity can be delayed without impacting the completion time of the project. True
The variance of the project completion time is equal to the sum of the variances of all the activities. False
The longest time path through a PERT/CPM network is called the critical path. True
Gantt charts contain information about the time taken by each activity, but not about the sequential dependencies of the activities. False

## Slide 2
1. Given an activity's optimistic, most likely, and pessimistic time estimates of 4, 6, and 14 days respectively, compute the PERT expected activity time for this activity.
A) 8
B) 6
C) 7
D) 9
2. Given an activity's optimistic, most likely, and pessimistic time estimates of 2, 10, and 20 days respectively, compute the PERT variance for this activity.
A) 3
B) 6
C) 9
D) 18

## Slide 4
b. What is the expected completion time for this project?
c. What is the critical path? Justify.
d. What variance would be used in finding probabilities of finishing by a given time?

## Slide 6
Activity | Immediate Predecessor | Optimistic | Most Likely | Pessimistic
A | - | 3 | 4 | 5
B | - | 6 | 7 | 14
C | A | 6 | 9 | 12
D | B | 0.5 | 1 | 1.5
E | B | 2 | 3 | 10
F | D,C | 4 | 5 | 12
G | E | 1 | 3 | 11