Quantitative Analysis for Management, 11e (Render)

Chapter 12   Project Management

1) PERT and CPM are quantitative analysis tools designed to schedule and control large projects.

Answer:  TRUE

Diff: 1

Topic:  INTRODUCTION

2) PERT is a deterministic analysis tool allowing for precise times of activities within a project.

Answer:  FALSE

Diff: 2

Topic:  INTRODUCTION

3) PERT had its beginnings in a military department of the United States.

Answer:  TRUE

Diff: 2

Topic:  PERT/CPM

4) CPM is a probabilistic analysis of managing a project.

Answer:  FALSE

Diff: 2

Topic:  INTRODUCTION

5) The first step in planning and scheduling a project is to develop the work breakdown structure.

Answer:  TRUE

Diff: 2

Topic:  INTRODUCTION

6) A PERT/CPM network is a graphical display of a project that connects activities.

Answer:  TRUE

Diff: 1

Topic:  PERT/CPM

7) The optimistic time is the greatest amount of time that could be required to complete an activity.

Answer:  FALSE

Diff: 2

Topic:  PERT/CPM

8) PERT is a network technique similar to CPM, but PERT allows for project crashing, whereas CPM does not.

Answer:  FALSE

Diff: 2

Topic:  PERT/CPM and PROJECT CRASHING

9) In PERT, the most likely completion time of an activity is used to represent that activity's time within a project.

Answer:  FALSE

Diff: 2

Topic:  PERT/CPM

10) The expected completion time and variance of an activity is approximated by the normal distribution in a PERT analysis.

Answer:  FALSE

Diff: 2

Topic:  PERT/CPM

11) PERT was developed for a project for which activity or task times were uncertain.

Answer:  TRUE

Diff: 2

Topic:  PERT/CPM

12) CPM was developed for use in managing projects about which we have good information about activity or task completion times.

Answer:  TRUE

Diff: 2

Topic:  PERT/CPM

13) With PERT, we are able to calculate the probability of finishing the project within a specified time.

Answer:  TRUE

Diff: 2

Topic:  PERT/CPM

14) With CPM, we are able to calculate the probability of finishing the project within a specified time.

Answer:  FALSE

Diff: 2

Topic:  PERT/CPM

15) Both PERT and CPM networks show activities and activity sequences.

Answer:  TRUE

Diff: 2

Topic:  PERT/CPM

16) The identification of the project activities and their time, cost, resource requirements, predecessors, and person(s) responsible is called PERT planning.

Answer:  FALSE

Diff: 2

Topic:  INTRODUCTION

17) Before drawing a PERT or CPM network, we must identify all activities and their predecessors.

Answer:  TRUE

Diff: 2

Topic:  PERT/CPM

18) The three time estimates employed in PERT are optimistic time, average time, and pessimistic time.

Answer:  FALSE

Diff: 2

Topic:  PERT/CPM

19) Given the variability of the activity completion times, the original critical path we identify in our PERT analysis may not always be the actual critical path as the project takes place.

Answer:  TRUE

Diff: 2

Topic:  PERT/CPM

20) In PERT, the earliest start time for an activity is equal to the latest of the earliest finish times of all of its immediate predecessors.

Answer:  TRUE

Diff: 2

Topic:  PERT/CPM

21) PERT stands for Probabilistic Evaluation and Review Technique.

Answer:  FALSE

Diff: 3

Topic:  INTRODUCTION

22) One of the most significant benefits of PERT is that it forces the project manager to sit down and plan the project in great detail—and thus come to an understanding of relationships between the activities.

Answer:  TRUE

Diff: 2

Topic:  PERT/CPM

23) Slack is the time an activity can be delayed without impacting the completion time of the project.

Answer:  TRUE

Diff: 2

Topic:  PERT/CPM

24) The variance of the project completion time is equal to the sum of the variances of all the activities.

Answer:  FALSE

Diff: 2

Topic:  PERT/CPM

25) In PERT, we assume that the project completion time can be modeled by the normal distribution.

Answer:  TRUE

Diff: 2

Topic:  PERT/CPM

26) One PERT/COST assumption is that money is spent at a constant rate over the time taken to complete an activity.

Answer:  TRUE

Diff: 2

Topic:  PERT/COST

27) CPM stands for Comprehensive Project Method.

Answer:  FALSE

Diff: 3

Topic:  INTRODUCTION

28) The longest time path through a PERT/CPM network is called the critical path.

Answer:  TRUE

Diff: 2

Topic:  INTRODUCTION

29) In CPM, crashing an activity that is not on the critical path increases the cost of the project.

Answer:  TRUE

Diff: 2

Topic:  PROJECT CRASHING

30) Through the use of PERT/CPM, astute managers can derive flexibility by identifying noncritical activities and replanning, rescheduling, and reallocating resources such as personnel and finances.

Answer:  TRUE

Diff: 2

Topic:  INTRODUCTION

31) In PERT, the variance in completion time is equal to the variance of the most time consuming activity on the critical path.

Answer:  FALSE

Diff: 2

Topic:  PERT/CPM

32) Given the assumptions in PERT, the probability that a project will be completed in less time than required by the activities on the critical path is approximately 50%.

Answer:  TRUE

Diff: 2

Topic:  PERT/CPM

33) Gantt charts and PERT diagrams provide the same information, just in different formats.

Answer:  FALSE

Diff: 2

Topic:  PERT/CPM

34) Gantt charts contain information about the time taken by each activity, but not about the sequential dependencies of the activities.

Answer:  TRUE

Diff: 2

Topic:  PERT/CPM

35) The critical path of a network is the

A) shortest time path through the network.

B) path with the fewest activities.

C) path with the most activities.

D) longest time path through the network.

E) None of the above

Answer:  D

Diff: 2

Topic:  INTRODUCTION

36) In a PERT network, the earliest (activity) start time is the

A) earliest time that an activity can be finished without delaying the entire project.

B) latest time that an activity can be started without delaying the entire project.

C) earliest time that an activity can start without violation of precedence requirements.

D) latest time that an activity can be finished without delaying the entire project.

E) None of the above

Answer:  C

Diff: 1

Topic:  PERT/CPM

37) Slack time in a network is the

A) amount of time that an activity would take assuming very unfavorable conditions.

B) shortest amount of time that could be required to complete the activity.

C) amount of time that you would expect it would take to complete the activity.

D) difference between the expected completion time of the project using pessimistic times and the expected completion time of the project using optimistic times.

E) amount of time that an activity can be delayed without delaying the entire project.

Answer:  E

Diff: 2

Topic:  PERT/CPM

38) The first step in planning and scheduling a project is to develop the ________.

A) employee scheduling plan

B) PERT/CPM network diagram

C) critical path

D) work breakdown structure

E) variance calculations for each activity

Answer:  D

Diff: 2

Topic:  INTRODUCTION

39) Which of the following is not a concept associated with CPM?

A) normal time

B) probability

C) normal cost

D) crash cost

E) deterministic network

Answer:  B

Diff: 2

Topic:  INTRODUCTION

40) PERT

A) assumes that we do not know ahead of time what activities must be completed.

B) assumes that activity time estimates follow the normal probability distribution.

C) is a network technique that uses three time estimates for each activity in a project.

D) is a deterministic network technique that allows for project crashing.

E) None of the above

Answer:  C

Diff: 2

Topic:  PERT/CPM

41) CPM

A) assumes we do not know ahead of time what activities must be completed.

B) assumes that activity time estimates follow the normal probability distribution.

C) is a deterministic network technique that allows for project crashing.

D) is a network technique that allows three time estimates for each activity in a project.

E) None of the above

Answer:  C

Diff: 2

Topic:  PERT/CPM

42) Managers use the network analysis of PERT and CPM to help them

A) derive flexibility by identifying noncritical activities.

B) replan, reschedule, and reallocate resources such as manpower and finances.

C) plan, schedule, monitor, and control large and complex projects.

D) All of the above

E) None of the above

Answer:  D

Diff: 2

Topic:  INTRODUCTION

43) The expected time in PERT is

A) a weighted average of the most optimistic time, most pessimistic time, and four times the most likely time.

B) the modal time of a beta distribution.

C) a simple average of the most optimistic, most likely, and most pessimistic times.

D) the square root of the sum of the variances of the activities on the critical path.

E) None of the above

Answer:  A

Diff: 2

Topic:  PERT/CPM

44) Given an activity's optimistic, most likely, and pessimistic time estimates of 4, 6, and 14 days respectively, compute the PERT expected activity time for this activity.

A) 8

B) 6

C) 7

D) 9

E) None of the above

Answer:  C

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

45) Given an activity's optimistic, most likely, and pessimistic time estimates of 2, 5, and 14 days respectively, compute the PERT expected activity time for this activity.

A) 6

B) 7

C) 9

D) 5

E) None of the above

Answer:  A

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

46) Given an activity's optimistic, most likely, and pessimistic time estimates of 4, 14, and 18 days respectively, compute the PERT expected activity time for this activity.

A) 14

B) 12

C) 11

D) 13

E) None of the above

Answer:  D

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

47) Given an activity's optimistic, most likely, and pessimistic time estimates of 2, 10, and 20 days respectively, compute the PERT variance for this activity.

A) 3

B) 6

C) 9

D) 18

E) None of the above

Answer:  C

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

48) Given an activity's optimistic, most likely, and pessimistic time estimates of 4, 12, and 18 days respectively, compute the PERT variance for this activity.

A) 2.33

B) 5.44

C) 8.00

D) 64.00

E) None of the above

Answer:  B

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

49) Given an activity's optimistic, most likely, and pessimistic time estimates of 3, 5, and 15 days, respectively, compute the PERT standard deviation for this activity.

A) 2

B) 4

C) 5

D) 15

E) None of the above

Answer:  A

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

50) Given the following small project, the critical path is ________ days.

| Activity | Immediate Predecessor | Time (days) |
| --- | --- | --- |
| A | - | 10 |
| B | - | 4 |
| C | A, B | 6 |

A) 10

B) 14

C) 16

D) 20

E) None of the above

Answer:  C

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

51) Given the following small project, the critical path is ________ days.

| Activity | Immediate Predecessor | Time (days) |
| --- | --- | --- |
| A | - | 8 |
| B | A | 4 |
| C | - | 10 |

A) 4

B) 10

C) 12

D) 22

E) None of the above

Answer:  C

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

Table 12-1

The following represents a project with know activity times. All times are in weeks.

| Activity | Immediate Predecessor | Time |
| --- | --- | --- |
| A | - | 4 |
| B | - | 3 |
| C | A | 2 |
| D | B | 7 |
| E | C, D | 4 |
| F | B | 5 |

52) Using the data in Table 12-1, what is the minimum possible time required for completing the project?

A) 8

B) 14

C) 25

D) 10

E) None of the above

Answer:  B

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

53) Using the data in Table 12-1, what is the latest possible time that C may be started without delaying completion of the project?

A) 0

B) 4

C) 8

D) 10

E) None of the above

Answer:  C

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

54) According to Table 12-1, compute the slack time for activity D.

A) 0

B) 5

C) 3

D) 6

E) None of the above

Answer:  A

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

55) Using the data in Table 12-1, compute the latest finish time for activity E.

A) 4

B) 10

C) 14

D) 25

E) None of the above

Answer:  C

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

Table 12-2

The following represents a project with four activities.  All times are in weeks.

| Activity | Immediate Predecessor | Optimistic Time | Most Likely Time | Pessimistic Time |
| --- | --- | --- | --- | --- |
| A | - | 2 | 8 | 14 |
| B | - | 8 | 8 | 8 |
| C | A | 6 | 9 | 18 |
| D | B | 5 | 11 | 17 |

56) According to the data in Table 12-2, what is the critical path?

A) A-B

B) A-C

C) B-D

D) A-B-C-D

E) None of the above

Answer:  C

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

57) According to the data in Table 12-2, what is the minimum expected completion time for the project?

A) 18

B) 19

C) 37

D) 11

E) None of the above

Answer:  B

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

58) According to Table 12-2, there are four activities in the project.  Assume the normal distribution is appropriate to use to determine the probability of finishing by a particular time.  If you wished to find the probability of finishing the project in 20 weeks or fewer, it would be necessary to find the variance and then the standard deviation to be used with the normal distribution.  What variance would be used?

A) 2

B) 4

C) 8

D) 12

E) None of the above

Answer:  B

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

59) According to Table 12-2, there are four activities in the project.  Assume the normal distribution is appropriate to use to determine the probability of finishing by a particular time.  What is the probability that the project is finished in 16 weeks or fewer? (Round to two decimals.)

A) 0.07

B) 0.93

C) 0.43

D) 0.77

E) None of the above

Answer:  A

Diff: 3

Topic:  PERT/CPM

AACSB:  Analytic Skills

60) Consider a project that has an expected completion time of 60 weeks and a standard deviation of five weeks.  What is the probability that the project is finished in 70 weeks or fewer? (Round to two decimals.)

A) 0.98

B) 0.48

C) 0.50

D) 0.02

E) 0.63

Answer:  A

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

61) Your company is considering submitting a bid on a major project.  You determine that the expected completion time is 100 weeks and the standard deviation is 10 weeks.  It is assumed that the normal distribution applies.  You wish to set the due date for the project such that there is an 85 percent chance that the project will be finished by this time.  What due date should be set?

A) 108.0

B) 110.4

C) 89.6

D) 85.0

E) 100

Answer:  B

Diff: 3

Topic:  PERT/CPM

AACSB:  Analytic Skills

Table 12-3

| Activity | Immediate Predecessor | Optimistic | Most Likely | Pessimistic | Standard Deviation | Variance |
| --- | --- | --- | --- | --- | --- | --- |
| A | -- | 4 | 5 | 6 | 0.333 | 0.111 |
| B | -- | 12 | 16 | 18 | 1.000 | 1.000 |
| C | A | 2 | 8 | 14 | 2.000 | 4.000 |
| D | A | 5 | 5 | 5 | 0.000 | 0.000 |
| E | B, C | 6 | 7 | 8 | 0.333 | 0.111 |

62) According to Table 12-3, there are five activities in a PERT project.  Which activities are on the critical path?

A) A-B-C-D-E

B) A-C-E

C) B-D

D) A-B-C-D

E) B-E

Answer:  E

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

63) According to Table 12-3, there are five activities in a PERT project.  What is the variance of the critical path?

A) 5.222

B) 4.222

C) 1.222

D) 0

E) 1.111

Answer:  E

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

64) According to Table 12-3, there are five activities in a PERT project.  If the normal distribution were used to find the probability of finishing this project in 24 weeks or fewer, what mean and variance would be used?

A) 20 and 4.222

B) 30 and 5.222

C) 20 and 5.222

D) 30 and 4.222

E) 22.667 and 1.111

Answer:  E

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

65) The critical path of a network is the

A) path with the least variance.

B) path with zero slack.

C) path with the most activities.

D) path with the largest variance.

E) None of the above

Answer:  B

Diff: 2

Topic:  PERT/CPM

66) In a PERT network, the latest (activity) start time is the

A) earliest time that an activity can be finished without delaying the entire project.

B) latest time that an activity can be started without delaying the entire project.

C) earliest time that an activity can start without violation of precedence requirements.

D) latest time that an activity can be finished without delaying the entire project.

E) None of the above

Answer:  B

Diff: 1

Topic:  PERT/CPM

67) The work breakdown structure involves identifying the ________ for each activity.

A) time

B) cost

C) resource requirements

D) predecessors

E) All of the above

Answer:  E

Diff: 2

Topic:  INTRODUCTION

68) PERT stands for ________.

A) probabilistic evaluation and review technique

B) program evaluation and review technique

C) probability of expected run times

D) program of expected run times

E) project evaluation and review technique

Answer:  B

Diff: 2

Topic:  INTRODUCTION

69) CPM stands for ________.

A) critical path management

B) critical project management

C) critical project method

D) critical path method

E) centralized project management

Answer:  D

Diff: 2

Topic:  INTRODUCTION

70) Which of the following questions can be answered by PERT?

A) When will the entire project be completed?

B) What is the probability that the project will be completed by a specific date?

C) What are the critical activities?

D) What are the noncritical activities?

E) All of the above

Answer:  E

Diff: 1

Topic:  PERT/CPM

71) In PERT, we assume that

A) the times to complete individual activities are known with certainty.

B) all activities are carried out by staff from our own organization.

C) the total cost of a project is independent of the time to complete the project.

D) the total time to complete all activities on the critical path is described by a normal distribution.

E) None of the above

Answer:  D

Diff: 2

Topic:  PERT/CPM

72) The two common techniques for drawing PERT networks are ________.

A) NOA and NRA

B) AON and AOA

C) GANTT and NOA

D) ONA and OAO

E) CAN and CAA

Answer:  B

Diff: 3

Topic:  PERT/CPM

73) In PERT analysis, the probability of the optimistic time occurring should be on the order of ________.

A) 1/2

B) 1/3

C) 1/6

D) 1/10

E) 1/100

Answer:  E

Diff: 2

Topic:  PERT/CPM

74) The expected time in PERT is

A) greater than the most likely time.

B) equal to the most likely time.

C) less than the most likely time.

D) any of the above

E) None of the above

Answer:  D

Diff: 2

Topic:  PERT/CPM

75) Given an activity's optimistic, most likely, and pessimistic time estimates of 3, 7, and 11 days respectively, compute the expected time for this activity.

A) 5

B) 6

C) 7

D) 12

E) None of the above

Answer:  C

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

76) Given an activity's optimistic, most likely, and pessimistic time estimates of 3, 5, and 13 days respectively, compute the expected time for this activity.

A) 3

B) 4

C) 5

D) 6

E) None of the above

Answer:  D

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

77) Given an activity's optimistic, most likely, and pessimistic time estimates of 1, 9, and 23 days respectively, compute the PERT expected activity time for this activity.

A) 10

B) 12

C) 9

D) 11

E) None of the above

Answer:  A

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

78) Given an activity's optimistic, most likely, and pessimistic time estimates of 3, 6, and 9 days respectively, compute the PERT variance for this activity.

A) 3

B) 1

C) 9

D) 6

E) None of the above

Answer:  B

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

79) The project described by:

| Activity | Immediate Predecessor | Time (days) |
| --- | --- | --- |
| A | -- | 10 |
| B | A | 4 |
| C | A | 6 |
| D | B | 7 |
| E | C | 5 |

is best represented by which of the following networks?

A)

B)

C)

D)

E) None of the above

Answer:  A

Diff: 1

Topic:  PERT/CPM

AACSB:  Analytic Skills

80) The project described by:

| Activity | Immediate Predecessor | Time (days) |
| --- | --- | --- |
| A | -- | 10 |
| B | A | 4 |
| C | A | 6 |
| D | B, C | 7 |
| E | C | 5 |

has a critical path of length of ________.

A) 21 days

B) 14 days

C) 23 days

D) 32 days

E) None of the above

Answer:  C

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

81) The project described by:

| Activity | Immediate Predecessor | Time (days) |
| --- | --- | --- |
| A | -- | 6 |
| B | A | 2 |
| C | -- | 8 |
| D | B, C | 5 |
| E | D | 7 |

has a critical path of length of ________.

A) 15 days

B) 20 days

C) 17 days

D) 18 days

E) None of the above

Answer:  B

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

Table 12-4

The following represents a project with known activity times. All times are in weeks.

| Activity | Immediate Predecessor | Time |
| --- | --- | --- |
| A | -- | 4 |
| B | -- | 3 |
| C | A | 2 |
| D | B | 7 |
| E | C, D | 4 |
| F | B | 5 |
| G | E, F | 4 |

82) Using the data in Table 12-4, what is the minimum possible time required for completing the project?

A) 8

B) 12

C) 18

D) 10

E) None of the above

Answer:  C

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

83) Using the data in Table 12-4, what is the latest possible time that C may be started without delaying completion of the project?

A) 0

B) 4

C) 8

D) 10

E) None of the above

Answer:  C

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

84) Using the data in Table 12-4, compute the slack time for activity D.

A) 0

B) 5

C) 3

D) 6

E) None of the above

Answer:  A

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

85) Using the data in Table 12-4, compute the latest finish time for activity E.

A) 4

B) 10

C) 14

D) 25

E) None of the above

Answer:  C

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

86) Using the data in Table 12-4, determine the latest time activity A can be started without delaying the project completion.

A) 4

B) 3

C) 8

D) 6

E) None of the above

Answer:  A

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

87) Using the data in Table 12-4, determine the latest time activity A can be finished and not delay any activity?

A) 4

B) 0

C) 8

D) 5

E) None of the above

Answer:  C

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

88) Consider a project that has an expected completion time of 50 weeks and a standard deviation of 9 weeks.  What is the probability that the project is finished in 57 weeks or fewer? (Round to two decimals.)

A) 0.68

B) 0.78

C) 0.22

D) 0.32

E) None of the above

Answer:  B

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

89) Your company is considering submitting a bid on a major project.  You determine that the expected completion time is 150 weeks and the standard deviation is 10 weeks.  It is assumed that the normal distribution applies.  You wish to set the due date for the project such that there is a 95 percent chance that the project will be finished by this time.  What due date should be set?

A) 108.0

B) 160.4

C) 166.5

D) 135.0

E) None of the above

Answer:  C

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

Table 12-5

| Activity | Immediate Predecessor | Time | ES | EF | LS | LF |
| --- | --- | --- | --- | --- | --- | --- |
| A | -- | 4 | 0 | 4 | 6 | 10 |
| B | -- | 5 | 0 | 5 | 0 | 5 |
| C | A | 3 | 4 | 7 | 10 | 13 |
| D | B | 8 | 5 | 13 | 5 | 13 |
| E | B | 2 | 5 | 7 | 16 | 18 |
| F | C, D | 3 | 13 | 16 | 15 | 18 |
| G | C, D | 7 | 13 | 20 | 13 | 20 |
| H | E, F | 2 | 16 | 18 | 18 | 20 |

90) How long could Table 12-5's activity E be delayed without delaying the completion of the project?

A) 7

B) 16

C) 11

D) 18

E) None of the above

Answer:  C

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

91) How long could Table 12-5's activity F be delayed without delaying the project?

A) 2

B) 3

C) 14

D) 16

E) None of the above

Answer:  A

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

92) What is the minimum possible time required for completing the Table 12-5 project?

A) 14

B) 18

C) 17

D) 20

E) None of the above

Answer:  D

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

Table 12-6

| Activity | Immediate Predecessor | Optimistic | Most Likely | Pessimistic | σ | σ2 |
| --- | --- | --- | --- | --- | --- | --- |
| A | -- | 2 | 3 | 4 | 0.333 | 0.111 |
| B | -- | 2 | 5 | 8 | 1.000 | 1.000 |
| C | A | 1 | 2 | 9 | 1.330 | 1.780 |
| D | A | 5 | 5 | 5 | 0.000 | 0.000 |
| E | B, C | 6 | 7 | 8 | 0.333 | 0.111 |
| F | B | 14 | 14 | 14 | 0.000 | 0.000 |
| G | D, E | 1 | 5 | 9 | 1.333 | 1.780 |
| H | G, F | 1 | 4 | 8 | 1.167 | 1.362 |

93) Which activities are part of Table 12-6's critical path?

A) A-B-E-G-H

B) A-C-E-G-H

C) A-D-G-H

D) B-F-H

E) None of the above

Answer:  D

Diff: 3

Topic:  PERT/CPM

AACSB:  Analytic Skills

94) What is the variance of Table 12-6's critical path?

A) 5.222

B) 4.364

C) 1.362

D) 5.144

E) 2.362

Answer:  E

Diff: 3

Topic:  PERT/CPM

AACSB:  Analytic Skills

Figure 12-1

95) Given the network in Figure 12-1, the critical path is

A) A-C-F-H.

B) B-D-E-F-H.

C) A-C-E-G-H.

D) B-D-G-E-F-H.

E) None of the above

Answer:  B

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

96) Given the network in Figure 12-1, the time to complete those activities on the critical path is expected to be ________.

A) 20

B) 22

C) 25

D) 26

E) None of the above

Answer:  C

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

97) Given the network shown in Figure 12-1, assume that completion of A is delayed by two days.  What other activities are impacted?

A) B

B) D

C) E

D) C

E) None of the above

Answer:  D

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

98) Given the network shown in Figure 12-1, assume that completion of B is delayed by two days.  What happens to the project?

A) The critical path is extended by two days.

B) The start of activity F is delayed by two days.

C) The start of activity E is delayed by two days.

D) All of the above

E) None of the above

Answer:  D

Diff: 2

Topic:  PERT/CPM

99) Given the network shown in Figure 12-1, assume that the completion of activity C is delayed by four days.  What changes will take place?

A) The critical path will change to: A-C-B-D-E-F-H.

B) Activity F will be delayed by four days.

C) Activity E will be delayed by four days.

D) Activity G will be delayed by four days.

E) None of the above

Answer:  E

Diff: 3

Topic:  PERT/CPM

AACSB:  Analytic Skills

100) Given the network shown in Figure 12-1 and the following information, what is the variance of the critical path?

| Activity | Expected time | Variance |
| --- | --- | --- |
| A | 3 | 2 |
| B | 5 | 3 |
| C | 6 | 3 |
| D | 4 | 1 |
| E | 5 | 1 |
| F | 4 | 2 |
| G | 6 | 2 |
| H | 7 | 2 |

A) 16

B) 7

C)  9

D)  8

E) None of the above

Answer:  C

Diff: 3

Topic:  PERT/CPM

AACSB:  Analytic Skills

101) PERT often assumes that time estimates follow which of the following probability distributions?

A) normal

B) exponential

C) binomial

D) Poisson

E) None of the above

Answer:  E

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

102) PERT assumes that the total completion time of a projects follows which of the following probability distributions?

A) normal

B) exponential

C) binomial

D) Poisson

E) None of the above

Answer:  A

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

103) The crash time of an activity represents

A) the normal time to complete an activity.

B) the most pessimistic time to complete an activity.

C) the incremental decrease in the time to complete an activity.

D) the shortened activity time.

E) None of the above

Answer:  D

Diff: 2

Topic:  PROJECT CRASHING

104) Reducing the overall activity time is based on which of the following steps?

A) crashing activities with the lowest overall crash cost

B) crashing activities with the lowest overall normal cost

C) crashing activities on the critical path based on lowest overall cost

D) crashing activities on the critical path based on lowest cost/week

E) crashing activities with the lowest cost/week.

Answer:  D

Diff: 2

Topic:  PROJECT CRASHING

105) An alternative approach to project crashing is to use which of the following techniques?

A) linear programming

B) nonlinear programming

C) Markov analysis

D) queuing theory

E) None of the above

Answer:  A

Diff: 2

Topic:  PROJECT CRASHING

106) Which of the following is not a decision variable when formulating the project crashing problem as a linear program?

A) the early finish times of critical activities

B) the early finish times of non critical activities

C) the start time of the project

D) the finish time of the project

E) the early start times of all activities

Answer:  E

Diff: 2

Topic:  PROJECT CRASHING

107) Which of the following statement about project crashing is false?

A) The crash cost is greater than or equal to the normal cost of an activity.

B) The crash time is less than or equal to the normal time to complete an activity.

C) Reducing the time of an activity on the critical path automatically reduces total project duration.

D) It may not be possible to crash a particular activity.

E) Crashing may not lead to an overall reduction in costs for the project.

Answer:  C

Diff: 3

Topic:  PROJECT CRASHING

108) The process of smoothing out the utilization of resources in a project is called

A) CPM.

B) PERT.

C) project crashing.

D) work breakdown structure.

E) resource leveling.

Answer:  E

Diff: 1

Topic:  OTHER TOPICS IN PROJECT MANAGEMENT

109) Consider the following project schedule:

| Activity | Immediate Predecessor | Time | ES | EF | LS | LF |
| --- | --- | --- | --- | --- | --- | --- |
| A | -- | 4 | 0 | 4 | 6 | 10 |
| B | -- | 5 | 0 | 5 | 0 | 5 |
| C | A | 3 | 4 | 7 | 10 | 13 |
| D | B | 8 | 5 | 13 | 5 | 13 |
| E | B | 2 | 5 | 7 | 16 | 18 |
| F | C, D | 3 | 13 | 16 | 15 | 18 |
| G | C, D | 7 | 13 | 20 | 13 | 20 |
| H | E, F | 2 | 16 | 18 | 18 | 20 |

(a)	Which activities are critical?

(b)	Which activity has the most slack?

Answer:  (a)	B, D, G

(b)	E

Diff: 1

Topic:  PERT/CPM

AACSB:  Analytic Skills

110) Consider the project with the following estimates for activity times and precedence relationships:

| Activity | Optimistic Time | Most Likely Time | Pessimistic Time | Immediate Predecessor(s) |
| --- | --- | --- | --- | --- |
| A | 3 | 4 | 5 | --- |
| B | 5 | 7 | 9 | --- |
| C | 2 | 3 | 10 | A |
| D | 2 | 5 | 8 | B |
| E | 1 | 7 | 7 | B |
| F | 3 | 5 | 7 | C, D |
| G | 7 | 8 | 9 | D, E |
| H | 2 | 6 | 10 | F |

(a)	What is the expected duration of the project?

(b)	What is the project variance?

(c)	If the deadline of the project is 25 days, what is the probability of finishing the project on time?

Answer:

(a)	23

(b)	3.67

(c)	0.8508

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

111) Consider the tasks, durations, and predecessor relationships in the following network. Draw the network and answer the questions that follow.

| Activity | Immediate Predecessors) | Optimistic (Weeks) | Most Likely (Weeks) | Pessimistic (Weeks) |
| --- | --- | --- | --- | --- |
| A | --- | 4 | 7 | 10 |
| B | A | 2 | 8 | 20 |
| C | A | 8 | 12 | 16 |
| D | B | 1 | 2 | 3 |
| E | D, C | 6 | 8 | 22 |
| F | C | 2 | 3 | 4 |
| G | F | 2 | 2 | 2 |
| H | F | 6 | 8 | 10 |
| I | E, G, H | 4 | 8 | 12 |
| J | I | 1 | 2 | 3 |

(a)  What is the expected duration of the project?

(b)  What is the probability of completion of the project before week 42?

Answer:

(a)  40

(b)  8079

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

112) Given:

| Activity | Optimistic | Most Likely | Pessimistic |
| --- | --- | --- | --- |
| A | 3 | 4 | 5 |
| B | 6 | 7 | 14 |
| C | 6 | 9 | 12 |
| D | 0.5 | 1 | 1.5 |
| E | 2 | 3 | 10 |
| F | 4 | 5 | 12 |
| G | 1 | 3 | 11 |

Determine:

(a)  the critical path.

(b)  the probability that the project will be completed in 22 weeks.

Answer:  (a)  Critical path is A-C-F. Expected time is 19.

(b)  Variance for critical path is 2.889, so standard deviation is 1.70.  P(X ≤ 22) = 0.9608

Diff: 3

Topic:  PERT/CPM

AACSB:  Analytic Skills

113) A small software development project has five major activities.  The times are estimated and provided in the table below.

| Activity | Immediate Predecessor | a | m | b |
| --- | --- | --- | --- | --- |
| A | -- | 2 | 5 | 8 |
| B | -- | 10 | 10 | 10 |
| C | A | 4 | 7 | 10 |
| D | B | 2 | 5 | 14 |
| E | C | 3 | 3 | 3 |

(a)  What is the expected completion time for this project?

(b)  What variance would be used in finding probabilities of finishing by a certain time?

Answer:

(a) expected completion time = 16  (Activities B-D)

(b) variance = 0 + 4 = 4

Diff: 3

Topic:  PERT/CPM

AACSB:  Analytic Skills

114) Development of a new deluxe version of a particular software product is being considered.  The activities necessary for the completion of this are listed in the table below (Time in weeks).

| Activity | Normal Time | Crash Time | Normal Cost | Crash Cost | Immediate Predecessor |
| --- | --- | --- | --- | --- | --- |
| A | 4 | 3 | 2200 | 2600 | -- |
| B | 2 | 1 | 2200 | 2800 | -- |
| C | 3 | 3 | 500 | 500 | -- |
| D | 8 | 4 | 2300 | 2600 | A |
| E | 6 | 3 | 900 | 1200 | B |
| F | 3 | 2 | 3000 | 4200 | C |
| G | 4 | 2 | 1400 | 2000 | D, E |

(a)  What is the project completion date?

(b)  What is the total cost required for completing this project on normal time?

(c)  If you wish to reduce the time required to complete this project by one week, which activity should be crashed, and how much will this increase the total cost?

Answer:

(a)  Project completion time = 16 weeks (Activities A-D-G)

(b)  Total cost = $12,300

(c)  Crash D, one week at an additional cost of $75

Diff: 3

Topic:  PERT/CPM and PROJECT CRASHING

AACSB:  Analytic Skills

115) Draw the PERT network associated with the following activities.

| Activity | Immediate Predecessor |
| --- | --- |
| A | -- |
| B | A |
| C | A |
| D | B |
| E | B |
| F | C, E |
| G | A, D |
| H | F |
| I | F |
| J | G, H, I |

Answer:

Diff: 2

Topic:  PERT/CPM

AACSB:  Analytic Skills

116) Given (Time in weeks):

| Activity | Optimistic | Most Likely | Pessimistic |
| --- | --- | --- | --- |
| A | 3 | 4 | 5 |
| B | 6 | 7 | 14 |
| C | 2 | 3 | 10 |
| D | 6 | 9 | 12 |
| E | 4 | 5 | 12 |
| F | 1 | 3 | 11 |
| G | 1 | 2 | 9 |
| H | 2 | 5 | 8 |
| I | 1 | 4 | 7 |

Determine:

(a)	the critical path.

(b)	the probability that the project will be completed in 22 weeks.

Answer:

(a)	Critical path is B-E-G-I.

(b)	Variance for critical path is 6.33; standard deviation is 2.51.  The probability that the project will be completed in 22 weeks = 0.65.

Diff: 3

Topic:  PERT/CPM

AACSB:  Analytic Skills

117) A small software development project has four major activities.  The times are estimated and provided in the table below.

| Activity | Immediate Predecessor | a | m | b |
| --- | --- | --- | --- | --- |
| A | -- | 2 | 5 | 8 |
| B | A | 3 | 6 | 9 |
| C | A | 4 | 7 | 10 |
| D | B | 2 | 5 | 14 |
| E | D | 3 | 3 | 3 |
| F | C | 6 | 8 | 10 |
| G | E, F | 1 | 1 | 1 |
| H | C | 6 | 10 | 14 |
| I | G, H | 3 | 4 | 5 |

(a)	What is the expected completion time for this project?

(b)	What variance would be used in finding probabilities of finishing by a certain time?

Answer:

(a) expected completion time = 26  (Activities A-C-H-I)

(b) variance = 3.88

Diff: 3

Topic:  PERT/CPM

AACSB:  Analytic Skills

118) Development of a new deluxe version of a particular software product is being considered.  The activities necessary for the completion of this are listed in the table below (Time in weeks).

| Activity | Immediate Predecessor | a | m | b |
| --- | --- | --- | --- | --- |
| A | -- | 2 | 5 | 8 |
| B | A | 3 | 6 | 9 |
| C | A | 4 | 7 | 10 |
| D | B | 2 | 5 | 14 |
| E | D | 3 | 3 | 3 |
| F | C | 6 | 8 | 10 |
| G | E, F | 1 | 1 | 1 |
| H | C | 6 | 10 | 14 |
| I | G, H | 3 | 4 | 5 |

(a)	If you wish to reduce the time required to complete this project by two weeks, which activity(ies) should be crashed, and how much will this increase the total cost?

(b)	What would be the added cost if you wanted to complete the project in the minimum time possible?

Answer:

(a)	Crash D, two weeks at an additional cost of $100

(b)	Crash D 4 weeks, G 2 weeks, E 3 weeks, A 1 week, and B 1 week, for a total additional cost of $1,700

Diff: 3

Topic:  PERT/CPM and PROJECT CRASHING

AACSB:  Analytic Skills

119) PERT is the acronym for what?

Answer:  Program Evaluation and Review Technique.

Diff: 2

Topic:  INTRODUCTION

120) In a PERT analysis, how is the optimistic time defined?

Answer:  the estimated time for an activity, should circumstances go as well as possible (should have a low probability of actual occurrence)

Diff: 2

Topic:  PERT/CPM

121) CPM is the acronym for what?

Answer:  Critical Path Method

Diff: 2

Topic:  INTRODUCTION

122) In PERT analysis, how is the pessimistic activity time defined?

Answer:  the estimated time for an activity, based on unfavorable conditions (should have a low probability of actual occurrence)

Diff: 2

Topic:  PERT/CPM

123) In PERT/CPM, what is meant by the critical path?

Answer:  the series of activities in a network that has zero slack or the longest time path through a network

Diff: 2

Topic:  PERT/CPM